## Blood Bank
BloodBank Tasks Schedule for Web Training
Week 1
Database analysis | laravelsd.com | TRUE
WebService analysis [APIs] |  | TRUE
Auth Cycle | includes ( notification settings and profile ) | TRUE
General Apis | governorates - cities - settings - contactus - categories - blood_types | TRUE
Week 2
Posts Cycle Api | posts - post - list favourites - toggle favourite | TRUE
Donations Cycle | donations - donation - create -includes (push notification) | TRUE
Week 3
Admin dashboard analysis |  | TRUE
prepare AdminLte for our project |  | TRUE
governorates module |  | TRUE
cities module |  | TRUE
categories module |  | TRUE
clients module | list&filter - delete - activate/de-activate | TRUE
posts module |  | TRUE
Week 4
contacts module | list&filter - delete | TRUE
donations module | list&filter - delete - show | TRUE
settings module | only edit | TRUE
change password page for admin |  | TRUE
users module |  | TRUE
roles module - Spatie | https://spatie.be/docs/laravel-permission/v5/introduction | TRUE
Automated Check Permission Middleware |  | TRUE
Week 5
home page | master & home | TRUE
Auth pages | login- register - profile - reset | TRUE
Donations | list - create - show | TRUE
Posts | list - toggle-favourite - list favourites | TRUE
General | about - contact